## AWS
# | Category | Task | Required? | Automated? | Documentation | Automation Tool | Level of Effort | Demo/Tutorial | Status | Progress Notes | Blockers
Milestone 1: Enablement
1 | Enablement | UC self-serve enablement | Required | Manual | N/A | N/A | Medium | N/A
2 | Enablement | Databricks account team UC enablement | Required | Manual | N/A | N/A | Low | N/A
Milestone 2: Assessment
3 | Assessment | UCX Assessment Tool - Run this tool to get a migration assessment - Share the dashboard with your account team by clicking on the 3 dots > download as PDF | Required | Automated | N/A | UCX Assessment | Low | UCX Assessment
Milestone 3: Activation
4 | Setup | Configure S3 bucket and IAM role for UC to store and access managed table | Required | Automated | Configure a storage bucket and IAM role in AWS | Terraform | Low | Setting up Unity Catalog (AWS)
5 | Setup | Create Metastore in Databricks account per region | Required | Automated | Configure your first metastore | Terraform | Low | Create a Unity Catalog Metastore in AWS
6 | Setup | Assign workspaces | Required | Automated | Assign workspaces | Terraform | Low | Create a Unity Catalog Metastore in AWS
7 | Setup | Identify and Assign main roles: - Account Admin - Metastore Admins - Workspace Admin | Required | Manual | Manage priviledges in Unity Catalog | N/A | Low | Create a Unity Catalog Metastore in AWS
Milestone 3: Upgrade - Identity
8 | Identity Federation | Set up SCIM provisioning with your identity provider | Optional | Manual | SCIM provisioning guide | N/A | Medium | N/A
9 | Upgrading Users, Groups, & Legacy Table ACLs | "Migrate user management and legacy ACLs from workspace to account level Run databricks UCX to create groups at account level - Run terraform or account UI to create account level groups - Run UCX job to rename workspace groups as a backup - Run UCX job to transfer ACLs from workspace to account groups - Run UCX to delete workspace groups - Check account level groups’ permission on existing cluster policies" | Required | Automated | Add users and groups | UCX Terraform | High | UCX user/group upgrade
Milestone 3: UC Design
10 | UC Design | Identify obsolete tables (empty, test tables, poc tables etc ) | Required | Automated | N/A | UCX Assessment | Low | N/A
11 | UC Design | Segregate tables into - Delta (External/managed), Parquet, Others | Required | Automated | N/A | UCX Assessment | Low | N/A
12 | UC Design | Define how to separate environments/team (workspace vs catalogs) | Required | Manual | Organize your data | N/A | Medium | N/A
13 | UC Design | Define UC catalogs - list of catalogs, naming conventions, catalog path Define Schema/databases | Required | Manual | N/A | N/A | Low | N/A
14 | UC Design | Identify requirements and strategy for external locations | Required | Manual | Manage external locations, external tables, and external volumes | N/A | Low | N/A
15 | UC Design | Catalog workspace isolation strategy (preview) | Optional | Manual | Assign a catalog to specific workspaces | N/A | Medium | N/A
16 | UC Design | Decide on target tables - will it be all external or manged to be cosnsistent across. | Required | Manual | Managed & external tables | N/A | Low | N/A
Milestone 4: Upgrade - Tables & External Locations
17 | External Locations | Create storage credentials and external locations | Required | Automated | Manage external locations and storage credentials | Terraform | Low | N/A
18 | Create Catalog | Catalog Creation (define the S3 path for catalog or let it be default) | Required | Automated | Create and manage catalogs | Terraform | Low | N/A
19 | Create Schema | Schema creation (define the S3 path for schema or let it be default) | Required | Automated | Create and manage schemas (databases) | Terraform | Low | N/A
20 | Upgrade Clusters | Create UC enabled clusters and validate UC is enabled | Required | Automated | Cluster access mode | Terraform | Low | N/A
21 | Upgrade External Tables | Upgrade external tables using CREATE TABLE LIKE, SYNC, or Upgrade Wizard | Required | Automated | CREATE TABLE LIKE SYNC Upgrade Wizard | UC Upgrade Notebook | High | N/A
22 | Upgrade Managed Tables | Upgrade managed tables using DEEP CLONE or CTAS | Required | Automated | DEEP CLONE CTAS | UC Upgrade Notebook | High | N/A
23 | Upgrade Views | Upgrade views | Required | Automated | Upgrade tables and views to Unity Catalog | UC Upgrade Notebook | Medium | N/A
Milestone 4: Upgrade - Workloads
25 | Upgrade workloads | Upgrade downstream DBSQL & BI queries to use the new catalog/database/table structure | Required | Manual | N/A | N/A | Medium | N/A
26 | Upgrade workloads | Upgrade Jobs - Use Assigned mode for jobs cluster - Set SP as owner of the prod jobs and run as that SP | Required | Both | Access modes | Job Upgrade Util - ask your account team | High | Upgrade jobs
27 | Upgrade workloads | Update jobs and notebooks to start using new Unity Catalog tables | Required | Both | N/A | Job Upgrade Util - ask your account team | High | N/A
28 | Upgrade workloads | Upgrade All Purpose Clusters - Use Assigned mode for MLR - Use Shared mode for most other use cases | Required | Manual | Access modes | N/A | High | Upgrade clusters
Milestone 5: Testing & Validation
29 | Validation | Validate the entire setup - Tables and data is fine - Jobs run fine - Creation of compute run fine - Any 3rd party tool accessing data/tables works fine - User permissions and access | Required | Manual | N/A | N/A | High | N/A
30 | Testing | Repeat all the steps/script from Test Env into Prod Env/Workspace | Required | Manual | N/A | N/A | High | N/A

## Azure
# | Category | Task | Required? | Automated? | Documentation | Automation Tool | Level of Effort | Demo/Tutorial | Status | Progress Notes | Blockers
Milestone 1: Enablement
1 | Enablement | UC self-serve enablement | Required | Manual | N/A | N/A | Medium | N/A
2 | Enablement | Databricks account team UC enablement | Required | Manual | N/A | N/A | Low | N/A
Milestone 2: Assessment
3 | Assessment | UCX Assessment Tool - Run this tool to get a migration assessment - Share the dashboard with your account team by clicking on the 3 dots > download as PDF | Required | Automated | N/A | UCX Assessment | Low | UCX Assessment
Milestone 3: Activation
4 | Setup | Configure ADLS bucket and IAM role for UC to store and access managed table | Required | Automated | Get started using Unity Catalog | Terraform | Low | Setting up Unity Catalog (Azure)
5 | Setup | Create Metastore in Databricks account per region | Required | Automated | Configure your first metastore | Terraform | Low | Create a Unity Catalog Metastore in Azure
6 | Setup | Assign workspaces | Required | Automated | Assign workspaces | Terraform | Low | Create a Unity Catalog Metastore in Azure
7 | Setup | Identify and Assign main roles: - Account Admin - Metastore Admins - Workspace Admin | Required | Manual | Manage priviledges in Unity Catalog | N/A | Low | Create a Unity Catalog Metastore in Azure
Milestone 3: Upgrade - Identity
8 | Identity Federation | Set up SCIM provisioning with your identity provider | Optional | Manual | SCIM provisioning guide | N/A | Medium | N/A
9 | Upgrading Users, Groups, & Legacy Table ACLs | Migrate user management and legacy ACLs from workspace to account level Run databricks UCX to create groups at account level - Run terraform or account UI to create account level groups - Run UCX job to rename workspace groups as a backup - Run UCX job to transfer ACLs from workspace to account groups - Run UCX to delete workspace groups - Check account level groups’ permission on existing cluster policies | Required | Automated | Add users and groups | UCX Terraform | High | UCX user/group upgrade
Milestone 3: UC Design
10 | UC Design | Identify obsolete tables (empty, test tables, poc tables etc ) | Required | Automated | N/A | UCX Assessment | Low | N/A
11 | UC Design | Segregate tables into - Delta (External/managed), Parquet, Others | Required | Automated | N/A | UCX Assessment | Low | N/A
12 | UC Design | Define how to separate environments/team (workspace vs catalogs) | Required | Manual | Organize your data | N/A | Medium | N/A
13 | UC Design | Define UC catalogs - list of catalogs, naming conventions, catalog path Define Schema/databases | Required | Manual | N/A | N/A | Low | N/A
14 | UC Design | Identify requirements and strategy for external locations | Required | Manual | Manage external locations, external tables, and external volumes | N/A | Low | N/A
15 | UC Design | Catalog workspace isolation strategy (preview) | Optional | Manual | Assign a catalog to specific workspaces | N/A | Medium | N/A
16 | UC Design | Decide on target tables - will it be all external or manged to be cosnsistent across. | Required | Manual | Managed & external tables | N/A | Low | N/A
Milestone 4: Upgrade - Tables & External Locations
17 | External Locations | Create storage credentials and external locations | Required | Automated | Manage external locations and storage credentials | Terraform | Low | N/A
18 | Create Catalog | Catalog Creation (define the ADLS path for catalog or let it be default) | Required | Automated | Create and manage catalogs | Terraform | Low | N/A
19 | Create Schema | Schema creation (define the ADLS path for schema or let it be default) | Required | Automated | Create and manage schemas (databases) | Terraform | Low | N/A
20 | Upgrade Clusters | Create UC enabled clusters and validate UC is enabled | Required | Automated | Cluster access mode | Terraform | Low | N/A
21 | Upgrade External Tables | Upgrade external tables using CREATE TABLE LIKE, SYNC, or Upgrade Wizard | Required | Automated | CREATE TABLE LIKE SYNC Upgrade Wizard | UC Upgrade Notebook | High | N/A
22 | Upgrade Managed Tables | Upgrade managed tables using DEEP CLONE or CTAS | Required | Automated | DEEP CLONE CTAS | UC Upgrade Notebook | High | N/A
23 | Upgrade Views | Upgrade views | Required | Automated | Upgrade tables and views to Unity Catalog | UC Upgrade Notebook | Medium | N/A
24 | Permissions & ACLs | Table ACL migration from HMS to UC | Required | Automated | UC priviledges and securable objects | UC Upgrade Notebook | Medium | N/A
Milestone 4: Upgrade - Workloads
25 | Upgrade workloads | Upgrade downstream DBSQL & BI queries to use the new catalog/database/table structure | Required | Manual | N/A | N/A | Medium | N/A
26 | Upgrade workloads | Upgrade Jobs - Use Assigned mode for jobs cluster - Set SP as owner of the prod jobs and run as that SP | Required | Both | Cluster access mode | Job Upgrade Util - ask your account team | High | Upgrade jobs
27 | Upgrade workloads | Update jobs and notebooks to start using new Unity Catalog tables | Required | Both | N/A | Job Upgrade Util - ask your account team | High | N/A
28 | Upgrade workloads | Upgrade All Purpose Clusters - Use Assigned mode for MLR - Use Shared mode for most other use cases | Required | Manual | Cluster access mode | N/A | High | Upgrade clusters
Milestone 5: Testing & Validation
29 | Validation | Validate the entire setup - Tables and data is fine - Jobs run fine - Creation of compute run fine - Any 3rd party tool accessing data/tables works fine - User permissions and access | Required | Manual | N/A | N/A | High | N/A
30 | Testing | Repeat all the steps/script from Test Env into Prod Env/Workspace | Required | Manual | N/A | N/A | High | N/A

## GCP
# | Category | Task | Required? | Automated? | Documentation | Automation Tool | Level of Effort | Demo/Tutorial | Status | Progress Notes | Blockers
Milestone 1: Enablement
1 | Enablement | UC self-serve enablement | Required | Manual | N/A | N/A | Medium | N/A
2 | Enablement | Databricks account team UC enablement | Required | Manual | N/A | N/A | Low | N/A
Milestone 2: Assessment
3 | Assessment | UCX Assessment Tool - Run this tool to get a migration assessment - Share the dashboard with your account team by clicking on the 3 dots > download as PDF | Required | Automated | N/A | UCX Assessment | Low | UCX Assessment
Milestone 3: Activation
4 | Setup | Configure GCS bucket and IAM role for UC to store and access managed table | Required | Automated | Get started using unity catalog | Terraform | Low | N/A
5 | Setup | Create Metastore in Databricks account per region | Required | Automated | Configure your first metastore | Terraform | Low | N/A
6 | Setup | Assign workspaces | Required | Automated | Assign workspaces | Terraform | Low | N/A
7 | Setup | Identify and Assign main roles: - Account Admin - Metastore Admins - Workspace Admin | Required | Manual | Manage priviledges in Unity Catalog | N/A | Low | N/A
Milestone 3: Upgrade - Identity
8 | Identity Federation | Set up SCIM provisioning with your identity provider | Optional | Manual | SCIM provisioning guide | N/A | Medium | N/A
9 | Upgrading Users, Groups, & Legacy Table ACLs | "Migrate user management and legacy ACLs from workspace to account level Run databricks UCX to create groups at account level - Run terraform or account UI to create account level groups - Run UCX job to rename workspace groups as a backup - Run UCX job to transfer ACLs from workspace to account groups - Run UCX to delete workspace groups - Check account level groups’ permission on existing cluster policies" | Required | Automated | Add users and groups | UCX Terraform | High | UCX user/group upgrade
Milestone 3: UC Design
10 | UC Design | Identify obsolete tables (empty, test tables, poc tables etc ) | Required | Automated | N/A | UCX Assessment | Low | N/A
11 | UC Design | Segregate tables into - Delta (External/managed), Parquet, Others | Required | Automated | N/A | UCX Assessment | Low | N/A
12 | UC Design | Define how to separate environments/team (workspace vs catalogs) | Required | Manual | Organize your data | N/A | Medium | N/A
13 | UC Design | Define UC catalogs - list of catalogs, naming conventions, catalog path Define Schema/databases | Required | Manual | N/A | N/A | Low | N/A
14 | UC Design | Identify requirements and strategy for external locations | Required | Manual | Manage external locations, external tables, and external volumes | N/A | Low | N/A
15 | UC Design | Catalog workspace isolation strategy (preview) | Optional | Manual | Assign a catalog to specific workspaces | N/A | Medium | N/A
16 | UC Design | Decide on target tables - will it be all external or manged to be cosnsistent across. | Required | Manual | Managed & external tables | N/A | Low | N/A
Milestone 4: Upgrade - Tables & External Locations
17 | External Locations | Create storage credentials and external locations | Required | Automated | Manage external locations and storage credentials | Terraform | Low | N/A
18 | Create Catalog | Catalog Creation (define the GCS path for catalog or let it be default) | Required | Automated | Create and manage catalogs | Terraform | Low | N/A
19 | Create Schema | Schema creation (define the GCS path for schema or let it be default) | Required | Automated | Create and manage schemas (databases) | Terraform | Low | N/A
20 | Upgrade Clusters | Create UC enabled clusters and validate UC is enabled | Required | Automated | Cluster access mode | Terraform | Low | N/A
21 | Upgrade External Tables | Upgrade external tables using CREATE TABLE LIKE, SYNC, or Upgrade Wizard | Required | Automated | CREATE TABLE LIKE SYNC Upgrade Wizard | UC Upgrade Notebook | High | N/A
22 | Upgrade Managed Tables | Upgrade managed tables using DEEP CLONE or CTAS | Required | Automated | DEEP CLONE CTAS | UC Upgrade Notebook | High | N/A
23 | Upgrade Views | Upgrade views | Required | Automated | Upgrade tables and views to Unity Catalog ¦ Databricks on AWS | UC Upgrade Notebook | Medium | N/A
24 | Permissions & ACLs | Table ACL migration from HMS to UC | Required | Automated | UC priviledges and securable objects | UC Upgrade Notebook | Medium | N/A
Milestone 4: Upgrade - Workloads
25 | Upgrade workloads | Upgrade downstream DBSQL & BI queries to use the new catalog/database/table structure | Required | Manual | N/A | N/A | Medium | N/A
26 | Upgrade workloads | Upgrade Jobs - Use Assigned mode for jobs cluster - Set SP as owner of the prod jobs and run as that SP | Required | Both | Cluster access mode | Job Upgrade Util - ask your account team | High | Upgrade jobs
27 | Upgrade workloads | Update jobs and notebooks to start using new Unity Catalog tables | Required | Both | N/A | Job Upgrade Util - ask your account team | High | N/A
28 | Upgrade workloads | Upgrade All Purpose Clusters - Use Assigned mode for MLR - Use Shared mode for most other use cases | Required | Manual | Cluster access mode | N/A | High | Upgrade clusters
Milestone 5: Testing & Validation
29 | Validation | Validate the entire setup - Tables and data is fine - Jobs run fine - Creation of compute run fine - Any 3rd party tool accessing data/tables works fine - User permissions and access | Required | Manual | N/A | N/A | High | N/A
30 | Testing | Repeat all the steps/script from Test Env into Prod Env/Workspace | Required | Manual | N/A | N/A | High | N/A